BRIEFED.

Daily News Quiz App

Complete Build Plan — Start to Launch

Platform: Android + Web (Flutter)

Timeline: ~30 Days to Launch

Monetization: Freemium (Free + Pro)

# 1. What Is Briefed?

Briefed is a daily 5-question news quiz app that makes users measurably smarter over time. It is personalized to each user's interests and region, tracks their knowledge growth, rewards consistency with streaks, and generates content people genuinely want to share on social media.

### Tagline

Stay Briefed. Stay Sharp.

### Target Audience

- Age 18–45 — students, young professionals, curious minds

- People who want to feel informed but don't have time to read full news

- Competitive people who enjoy daily challenges and tracking progress

### Platforms

- Android (primary — launch first)

- Web via Flutter Web (launch together with Android)

- iOS (later — after validating traction)

### Core Loop

Every day at a set time, 5 questions drop based on real news from the last 24 hours. User answers, gets a score, sees where they rank globally, and shares their result. Tomorrow it resets. That is the addiction loop.

# 2. Complete Feature List

## 2.1 Free Tier Features

- 1 quiz per day (5 questions)

- Auto-detected regional news + chosen interest categories

- 15-second timer per question

- Instant correct/wrong feedback with answer highlight

- Story Behind the Question — 3-sentence AI summary after each answer

- Daily streak tracking

- Knowledge Score (cumulative points, never resets)

- Global percentile rank — Top X% today

- Daily result shareable card

- Hot Take — daily opinion poll with global results

- Did You Know — daily shareable fact card

- Daily push notification at user-chosen time

- Guest mode (limited — no streak sync across devices)

## 2.2 Pro Tier Features

- Everything in Free

- Unlimited quiz replay — retake today's quiz

- Streak Freeze — save your streak once per month if you miss a day

- Full AI explanations for every answer

- Deep progress analytics — category performance breakdown

- Full quiz archive — play any past day's quiz

- Weekly News Personality Card — shareable personality label

- Monthly Wrapped — Spotify-style monthly stats card

- No ads

## 2.3 Social Sharing Mechanics

| Share Type | Frequency | Hook |
| --- | --- | --- |
| Daily Result Card | Every day | Score + streak + global rank |
| Hot Take Poll | Every day | Opinion + global split data |
| Did You Know Fact | Every day | Interesting fact from today's news |
| Weekly Personality Card | Every Sunday | Tech Hawk, World Wanderer, etc. |
| Monthly Wrapped | End of month | Full stats like Spotify Wrapped |
| Streak Milestone Card | 7, 30, 50, 100 days | Achievement flex |
| Hardest Question Challenge | Every day | Only 9% got this right — can you? |

## 2.4 Gamification

Knowledge Score

- Easy correct answer: +10 points

- Hard correct answer: +25 points

- 7+ day streak bonus: +50 points per quiz

- Cumulative — never resets — becomes the user's identity

Streak System

- Counts consecutive days completing the quiz

- Missing one day resets to 0 — creates urgency

- Streak Freeze (Pro only) — saves streak if user misses one day per month

Badges

| Badge | How to Earn |
| --- | --- |
| On Fire | 7 day streak |
| Dedicated | 30 day streak |
| Legend | 100 day streak |
| Perfect Day | Score 5/5 |
| Genius Week | Score 5/5 every day for a week |
| Well Rounded | Answer correctly in all 6 categories |
| Rare Find | Answer a question only 5% of users got right |

# 3. All App Screens

## 3.1 Splash Screen

- App logo + tagline animation

- Check if user is logged in

- Route to onboarding (new user) or home (returning user)

## 3.2 Onboarding — 3 Steps

Step 1 — Pick Interests

- User selects news categories: World, Tech, Sports, Science, Business, Entertainment

- Minimum 2 required

- These feed the AI question pipeline

Step 2 — Set Daily Reminder

- Pick notification time (e.g. 8:00 AM)

- Get notified when today's quiz is ready

Step 3 — Create Account

- Sign in with Google (highest conversion)

- Or continue as guest (limited features, no streak sync)

## 3.3 Home Screen

- Today's Quiz Card — big, prominent, shows categories included today

- Streak counter and Knowledge Score display

- Did You Know — today's shareable fact card

- Stats row — quizzes done, best score, this week

- Countdown timer if quiz not yet available

- Bottom navigation — Home, Explore, Profile

## 3.4 Quiz Screen

- Progress bar (Question X of 5)

- Category pill and difficulty indicator

- Question text — clear, bold

- 4 answer options as tappable cards

- 15-second circular timer per question

- Tap answer — instant green (correct) or red (wrong) feedback

- Correct answer always highlights even if user got it wrong

- Story Behind the Question card slides up after answering

- Next Question / See Results button

## 3.5 Results Screen

- Score: X/5 with performance label

- Streak update and Knowledge Score delta

- Stats row — streak, points earned, global rank

- Shareable result card preview with one-tap share

- Hot Take button — go to today's opinion poll

- Review Answers button — see all 5 with explanations

- Back to Home button

## 3.6 Hot Take Screen

- Bold daily question — not politics, focuses on tech/society/culture

- YES / NO vote buttons with glassy icons

- After voting — animated bar chart showing global split

- Total voters count

- Shareable opinion card — I voted YES and 61% agree

- Back to Home button

## 3.7 Profile / Progress Screen

- Avatar, username, member since date

- Current streak and total Knowledge Score

- Knowledge Score line graph — growth over time

- Category breakdown — strongest vs weakest

- Streak heatmap calendar — GitHub contribution style

- Badges earned display

- Quiz history — last 30 days

## 3.8 Settings Screen

- Edit interest categories

- Change notification time

- Account settings — name, avatar

- Upgrade to Pro

- Privacy policy and terms links

# 4. Tech Stack

| Layer | Technology | Purpose | Cost |
| --- | --- | --- | --- |
| Frontend | Flutter | Android + Web from one codebase | Free |
| State Management | Riverpod | Clean, scalable state management | Free |
| Navigation | GoRouter | Declarative routing for Flutter | Free |
| Backend | Firebase | Auth, database, cloud functions | Free tier |
| Database | Firestore | Real-time, scalable NoSQL database | Free tier |
| Auth | Firebase Auth + Google Sign-In | Easy one-tap login | Free |
| AI Questions | Gemini 1.5 Flash API | Generate quiz questions from headlines | Free tier |
| News Source | NewsData.io API | Real headlines by country + category | Free: 200 req/day |
| Notifications | Firebase Cloud Messaging | Daily quiz push notifications | Free |
| Web Hosting | Firebase Hosting | Host Flutter web version | Free |
| Sharing | screenshot + share_plus | Generate and share result images | Free |
| Storage | shared_preferences | Cache questions and user data locally | Free |

## 4.1 Flutter Packages (pubspec.yaml)

flutter_riverpod: ^2.5.1      # State management

go_router: ^13.2.0            # Navigation

firebase_core: ^2.30.1        # Firebase setup

firebase_auth: ^4.19.5        # Authentication

cloud_firestore: ^4.17.2      # Database

firebase_messaging: ^14.9.1   # Push notifications

google_sign_in: ^6.2.1        # Google login

google_fonts: ^6.2.1          # Poppins font

screenshot: ^2.3.0            # Capture share card

share_plus: ^9.0.0            # Native share sheet

shared_preferences: ^2.2.3    # Local cache

dio: ^5.4.3                   # HTTP requests

fl_chart: ^0.67.0             # Progress graphs

intl: ^0.19.0                 # Date formatting

lottie: ^3.1.0                # Animations

# 5. Project Folder Structure

lib/

main.dart                   # Entry point

app.dart                    # App widget + theme + router

core/

theme/

app_theme.dart          # Colors, fonts, text styles

app_colors.dart         # All color constants

router/

app_router.dart         # All routes defined here

constants/

app_constants.dart      # API keys, strings, enums

features/

auth/

screens/

splash_screen.dart

onboarding_screen.dart

login_screen.dart

controllers/

auth_controller.dart

quiz/

models/

question_model.dart

quiz_result_model.dart

screens/

home_screen.dart

quiz_screen.dart

result_screen.dart

hot_take_screen.dart

review_screen.dart

controllers/

quiz_controller.dart

widgets/

question_card.dart

timer_ring.dart

story_card.dart

share_card.dart

option_button.dart

profile/

screens/

profile_screen.dart

settings_screen.dart

controllers/

profile_controller.dart

widgets/

streak_calendar.dart

score_chart.dart

badge_grid.dart

notifications/

notification_service.dart

shared/

widgets/

glass_card.dart         # Reusable glass card

icon_badge.dart         # Glassy icon container

category_pill.dart      # Category tag

primary_button.dart     # Orange gradient button

ghost_button.dart       # Outlined button

services/

firestore_service.dart  # All Firestore calls

auth_service.dart       # Auth logic

quiz_service.dart       # Fetch today's quiz

models/

user_model.dart

functions/

index.js                    # Cloud Functions

package.json

quiz_prompt.txt               # Gemini prompt (complete)

# 6. Firestore Data Structure

## 6.1 Users Collection

users/

{userId}/

name: string

email: string

country: string           # Auto-detected (e.g. 'in', 'ke', 'au')

categories: string[]      # ['world', 'tech', 'business']

notificationHour: int     # 8 = 8:00 AM

fcmToken: string          # Push notification token

streak: int

longestStreak: int

knowledgeScore: int

lastPlayedDate: timestamp

badges: string[]

isPro: bool

createdAt: timestamp

## 6.2 Quizzes Collection

quizzes/

{date}/                     # e.g. '2024-04-16'

metadata/

generatedAt: timestamp

totalPlayers: int

published: bool

questions/

q1/

question: string

options: string[]     # 4 options

correctIndex: int

explanation: string

storySummary: string  # 3 sentences

source: string

category: string

difficulty: string    # 'easy' or 'hard'

q2/ ... q5/

scores/

{userId}/

score: int            # 0-5

pointsEarned: int

timeTaken: int        # seconds

completedAt: timestamp

## 6.3 HotTakes Collection

hotTakes/

{date}/

question: string

yesVotes: int

noVotes: int

votes/

{userId}: 'yes' | 'no'

# 7. AI Question Pipeline

## 7.1 How It Works (Automated)

The entire question generation process runs automatically every morning with zero manual work required after initial setup.

- 6:00 AM — Firebase Cloud Function triggers automatically

- NewsData.io API fetches top headlines filtered by country + categories

- Headlines and summaries are sent to Gemini 1.5 Flash API with the quiz prompt

- Gemini returns 5 MCQ questions in clean JSON format

- Duplicate check — compare question hash against last 30 days in Firestore

- Questions stored in Firestore under today's date

- 7:00 AM — Quiz goes live for all users

- Firebase Cloud Messaging sends push notification to all users

## 7.2 Regional Personalization

Questions are NOT the same for everyone. The pipeline generates personalized questions based on each user's country and selected categories.

A user in Kenya with Tech + Business interests gets: Kenyan tech headlines + East Africa business news + 2 global stories. They never see Australian sports or US politics unless they choose to.

NewsData.io API Call Example

GET https://newsdata.io/api/1/news

?apikey=YOUR_KEY

&country=ke              # Kenya

&language=en

&category=technology,business

&size=10

## 7.3 Question Mix Per Quiz

| Questions | Source | Purpose |
| --- | --- | --- |
| Q1, Q2 | Local/regional news | Relevant to user's country |
| Q3 | User's top interest category | Personally relevant |
| Q4, Q5 (Hard) | Global top stories | Globally aware + challenging |

## 7.4 Gemini System Prompt (Full)

This is the exact prompt used in your Cloud Function. Save this in quiz_prompt.txt in your project.

You are a quiz question generator for a daily news app called Briefed.

Generate engaging, accurate, fair multiple choice questions from real news.

STRICT RULES:

1. Generate EXACTLY 5 questions

2. Questions 1-3 = EASY (answerable from headline alone)

3. Questions 4-5 = HARD (require deeper story understanding)

4. Each question has EXACTLY 4 answer options

5. Wrong answers must be BELIEVABLE and PLAUSIBLE

6. Never ask about exact dates, percentages, or obscure statistics

7. Keep every question under 20 words

8. Never generate two questions from the same headline

9. Return ONLY valid raw JSON — no markdown, no backticks

10. Start response with { and end with }

WRONG ANSWER RULES:

- Use real countries in same region for 'which country' questions

- Use real competitors for 'which company' questions

- A smart person who did not read the story should consider them

CONTENT RULES:

- Never ask about death tolls, tragedy specifics, graphic events

- Stay politically neutral — factual only

- For disasters — ask about policy response, not victims

JSON FORMAT:

{

"questions": [

{

"question": "...",

"options": ["A", "B", "C", "D"],

"correct_index": 0,

"difficulty": "easy",

"category": "Tech",

"explanation": "2-3 sentence explanation",

"story_summary": "Exactly 3 sentence story summary",

"source": "BBC News"

}

]

}

## 7.5 Failure Handling

- Keep a 3-day buffer of pre-generated questions in Firestore

- If NewsData.io API fails — deploy previous day's backup automatically

- If Gemini returns invalid JSON — retry up to 3 times with same headlines

- Flag system — if 3+ users flag the same question, auto-pull it and notify you

- Admin panel (simple Flutter Web page) to review and approve questions before publish

# 8. Ranking & Scoring System

## 8.1 Daily Rank

- Resets every day at midnight

- Based on score (0-5) first, then time taken as tiebreaker

- Two users score 4/5 — whoever finished faster ranks higher

- Displayed as Top X% — calculated from Firestore scores

Percentile Calculation

usersBelow = count of today's scores < userScore

totalPlayers = total who played today

percentile = round((usersBelow / totalPlayers) * 100)

display = 'Top ' + (100 - percentile) + '%'

## 8.2 All-Time Knowledge Score

- Cumulative — never resets — becomes user identity

- Easy correct answer: +10 points

- Hard correct answer: +25 points

- 7-day streak bonus: +50 points per quiz

- Displayed on profile, home screen, and share cards

- Drives long-term retention — users want to keep growing it

# 9. Sharing Implementation

## 9.1 How Share Cards Work in Flutter

Every shareable card is a Flutter widget wrapped in a RepaintBoundary. When the user taps Share, the widget is captured as a PNG image and sent to the native share sheet. Zero backend needed.

Step 1 — Wrap Card in RepaintBoundary

final _shareKey = GlobalKey();

RepaintBoundary(

key: _shareKey,

child: ShareCardWidget(

score: score,

streak: streak,

percentile: percentile,

),

)

Step 2 — Capture and Share

Future<void> shareResult() async {

final boundary = _shareKey.currentContext!

.findRenderObject() as RenderRepaintBoundary;

final image = await boundary.toImage(pixelRatio: 3.0);

final bytes = await image.toByteData(

format: ImageByteFormat.png),

final dir = await getTemporaryDirectory();

final file = File('${dir.path}/briefed_result.png');

await file.writeAsBytes(bytes!.buffer.asUint8List());

await Share.shareXFiles(

[XFile(file.path)],

text: 'I scored $score/5 on Briefed! #Briefed',

);

}

## 9.2 Share Card Designs

| Card Type | Content | When Shown |
| --- | --- | --- |
| Daily Result | Score, streak, global rank, date, hashtags | After every quiz |
| Hot Take | Vote + global percentage split | After voting |
| Did You Know | Fact + app branding | Home screen daily |
| Weekly Personality | Personality label + week stats | Every Sunday |
| Monthly Wrapped | Full month stats + highlights | End of month |
| Streak Milestone | Days count + total questions answered | 7, 30, 50, 100 days |

# 10. Monetization Strategy

## 10.1 Pricing

| Plan | Price | Platform |
| --- | --- | --- |
| Free | Forever free | Android + Web |
| Pro Monthly | ₹149/month or $2.99/month | Android + Web |
| Pro Annual | ₹999/year or $19.99/year (save 44%) | Android + Web |

The $99 Apple Developer fee pays for itself if just 34 people subscribe at $2.99/month. Wait until Android + Web shows traction before paying for iOS.

## 10.2 Freemium Gate Strategy

The free tier must be genuinely good — not crippled. Users should get real value for free and upgrade because they want more, not because the app is broken without Pro.

- Free gives the full daily experience — quiz, streak, score, sharing

- Pro removes friction and adds depth — replays, analytics, archive, Wrapped

- Streak Freeze is the single most powerful Pro conversion driver — users panic when they have a 30-day streak and miss a day

## 10.3 Future Revenue Streams

- Sponsored quiz categories — Today's Tech Quiz brought to you by [Brand]

- Brand trivia rounds — companies pay to be featured in a special quiz

- B2B corporate plan — companies subscribe for employees to stay informed

- All of these are realistic once you reach 10,000+ daily active users

# 11. Complete Build Phases

## Phase 0 — Accounts & Setup (Day 1)

Accounts to Create

- firebase.google.com — Create new project called 'briefed-app'

- newsdata.io — Sign up for free account, get API key

- aistudio.google.com — Get Gemini API key

- play.google.com/console — Already paid ($25)

Tools to Install

- Flutter SDK — flutter.dev/docs/get-started/install

- VS Code + Flutter + Dart extensions

- Android Studio (for Android emulator)

- Node.js (for Firebase Cloud Functions)

- Firebase CLI — npm install -g firebase-tools

- FlutterFire CLI — dart pub global activate flutterfire_cli

Create Flutter Project

flutter create briefed

cd briefed

flutterfire configure

firebase init functions

flutterfire configure automatically links your Flutter app to Firebase and generates google-services.json for Android.

## Phase 1 — Test The AI Pipeline (Day 2)

CRITICAL: Do this before writing any Flutter code. If questions are bad, nothing else matters.

Step 1 — Test NewsData.io

Open this URL in your browser (replace YOUR_KEY):

https://newsdata.io/api/1/news?apikey=YOUR_KEY

&country=in&language=en&category=technology,world&size=5

Check: Are headlines fresh? Relevant? From today?

Step 2 — Test Gemini in AI Studio

- Go to aistudio.google.com

- Click Create new prompt

- Select Gemini 1.5 Flash as the model

- Paste the System Instructions from Section 7.4 into the System box

- Paste 5 real headlines from NewsData.io into the user message

- Click Run

- Judge the output — are questions clear, fair, and interesting?

- Tweak the system instructions until you are happy

- Run 5-6 times with different headlines to confirm consistency

Step 3 — Test With Different Regions

Kenya:     &country=ke&language=en

Australia: &country=au&language=en

UK:        &country=gb&language=en

India:     &country=in&language=en

Confirm questions feel locally relevant for each region.

Only move to Phase 2 once questions consistently look excellent. This phase takes 1-2 hours and saves weeks of problems later.

## Phase 2 — App Foundation (Days 3–5)

- Create folder structure exactly as shown in Section 5

- Add all packages to pubspec.yaml as shown in Section 4.1

- Create app_colors.dart with all colors from the design system

- Create app_theme.dart with ThemeData — Poppins font, all text styles

- Create app_router.dart with GoRouter — all named routes

- Set up main.dart with ProviderScope and Firebase.initializeApp()

- Test that app runs on Android emulator with no errors

Design System Colors

primary:       #FF6B35   // Orange

background:    #0A0714   // Deep dark

surface:       rgba(255,255,255,0.055)  // Glass

correct:       #22C55E   // Green

wrong:         #EF4444   // Red

textPrimary:   #FFFFFF

textSecondary: rgba(255,255,255,0.4)

accent:        #A855F7   // Purple

## Phase 3 — Auth & Onboarding (Days 6–8)

- Build splash screen — logo animation + auth check routing

- Build Google Sign-In with firebase_auth + google_sign_in packages

- Build guest mode — store progress with shared_preferences

- Build onboarding step 1 — category selection grid (6 categories)

- Build onboarding step 2 — notification time picker

- Build onboarding step 3 — account creation / guest continue

- Save user document to Firestore on signup (structure from Section 6.1)

- Auto-detect user country from device locale

- Test full onboarding flow end-to-end

Build guest mode properly from Day 1. A large percentage of users will not sign in immediately. Make the app fully usable as a guest with a gentle nudge to sign in after the first quiz.

## Phase 4 — Quiz Engine (Days 9–13)

The most important phase. Build it carefully and test every interaction.

- Create Question model and QuizResult model (see Section 6.2 for fields)

- Build QuizController with Riverpod — loads questions, tracks answers, manages timer

- Build quiz screen layout — progress bar, category pill, question text

- Build OptionButton widget — 4 options, tap feedback, disabled state

- Implement answer tap logic — select, show correct/wrong, disable all other options

- Build circular timer ring widget — SVG-style countdown, changes color under 5 seconds

- Build StoryCard widget — slides up after answering with 3-sentence summary

- Implement Next Question navigation with state reset

- Handle last question — navigate to results screen with answers array

- Test full quiz flow 20 times — catch edge cases

Timer Implementation

// Reset timer on each new question

ref.listen(currentQuestionProvider, (prev, next) {

_timer?.cancel();

_timeLeft = 15;

_timer = Timer.periodic(Duration(seconds: 1), (t) {

if (_timeLeft <= 0 || _answered) { t.cancel(); return; }

state = state.copyWith(timeLeft: --_timeLeft);

});

});

## Phase 5 — Results & Sharing (Days 14–17)

- Build results screen — score display, stats row, performance label

- Calculate and display global percentile rank from Firestore

- Update user's streak, knowledge score, lastPlayedDate in Firestore

- Update quiz's totalPlayers count and scores subcollection

- Build ShareCardWidget — daily result card design

- Implement RepaintBoundary capture + share_plus sharing

- Build Hot Take screen — question, YES/NO buttons, animated results bar

- Build Hot Take share card

- Build Review Answers screen — all 5 questions with explanations

- Test sharing on physical device — WhatsApp, Instagram, Messages

## Phase 6 — Streaks & Gamification (Days 18–20)

- Implement streak check logic on every app open

- Implement streak reset on missed day

- Build streak milestone detection — 7, 30, 50, 100 days

- Build milestone share card widget

- Implement badge award logic — check after every quiz completion

- Build badge display grid on profile screen

- Implement Weekly Personality Card generation (Pro)

- Implement Monthly Wrapped generation (Pro)

- Test streak edge cases — midnight, timezone, missed days

## Phase 7 — Cloud Functions & Notifications (Day 21)

- Write generateDailyQuiz Cloud Function — fetch news, call Gemini, store to Firestore

- Write duplicate check logic — hash comparison against last 30 days

- Write sendDailyNotifications Cloud Function — runs hourly, sends to users by notification time

- Set up FCM token saving in Flutter on app launch

- Request notification permission in onboarding

- Test full pipeline locally with firebase emulators:start

- Deploy Cloud Functions to Firebase

- Verify questions generate correctly in production Firestore

Cloud Function Schedule

// Generate quiz at 6 AM UTC daily

exports.generateDailyQuiz = functions.pubsub

.schedule('0 6 * * *')

.timeZone('UTC')

.onRun(async (context) => { ... });

// Send notifications hourly

exports.sendNotifications = functions.pubsub

.schedule('0 * * * *')

.onRun(async (context) => { ... });

## Phase 8 — Web Version (Days 22–24)

- Run flutter build web to test current state

- Wrap all screens in ConstrainedBox(maxWidth: 480) for desktop web

- Add web-specific meta tags in web/index.html — OG image, description, title

- Build web landing page — brief description + Download on Play Store button

- Make shareable result links work on web — open today's quiz for recipient

- Deploy to Firebase Hosting — firebase deploy --only hosting

- Buy domain — briefedapp.com or getbriefed.app (~$12/year)

- Connect custom domain in Firebase Hosting

- Test on Chrome, Safari, Firefox, and mobile browsers

Flutter Web Deploy Commands

flutter build web --release

firebase deploy --only hosting

# App live at: your-project.web.app

# After custom domain: briefedapp.com

## Phase 9 — Polish & Testing (Days 25–28)

Performance Optimizations

- Cache today's questions locally on first load — no spinner on quiz start

- Preload next question's data while user reads story card

- Implement offline mode — show cached quiz, sync when back online

- Lazy load profile graphs — only render when user navigates to profile

Edge Cases to Handle

- User plays at 11:58 PM — questions expire at midnight — handle gracefully

- New user Day 1 — no streak yet — show 'Start your streak today'

- API fails — deploy backup questions automatically

- No internet — show cached quiz, sync results later

- User changes timezone — streak calculation must still be correct

- First-time share on iOS — permission prompt

Testing Checklist

- Full onboarding flow from scratch

- Google Sign-In works on physical device

- Questions load correctly for different regions

- Timer counts down accurately

- Score calculates correctly

- Streak increments and resets correctly

- Share card generates and shares on WhatsApp and Instagram

- Notifications arrive at correct time

- Web version loads and works on mobile browser

- App works fully offline after first load

- Handles no-internet gracefully

## Phase 10 — Play Store Launch (Days 29–30)

Assets to Create

- App icon — 1024x1024 PNG — orange background, white B logo

- Feature graphic — 1024x500 PNG — shows key screens

- 8 phone screenshots — show onboarding, home, quiz, results, profile

- Privacy policy page — host on Firebase Hosting at /privacy

Play Store Listing

App name:          Briefed - Daily News Quiz

Short description: Test your knowledge with today's top news. 5 questions daily.

Category:          News & Magazines or Education

Content rating:    Everyone

Keywords:          news quiz, daily quiz, current events, trivia, world news

Launch Day Actions

- Submit to Play Store — review takes 2-7 days

- Post on Reddit: r/androidapps, r/InternetIsBeautiful, r/mildlyinteresting

- Submit to Product Hunt

- Post on Twitter/X + LinkedIn — 'I built Wordle for news'

- Share with personal WhatsApp contacts — first 50 users

- Post the 'Hardest Question' challenge on social media

# 12. Timeline Summary

| Phase | What You Build | Days | Done? |
| --- | --- | --- | --- |
| 0 | Accounts, tools, Flutter project setup | 1 | [ ] |
| 1 | Test AI pipeline in Google AI Studio | 1 | [ ] |
| 2 | App foundation — structure, theme, router | 3 | [ ] |
| 3 | Auth, Google Sign-In, onboarding flow | 3 | [ ] |
| 4 | Quiz engine — questions, timer, feedback | 5 | [ ] |
| 5 | Results screen, sharing, Hot Take | 4 | [ ] |
| 6 | Streaks, badges, gamification, Wrapped | 3 | [ ] |
| 7 | Cloud Functions, AI pipeline, notifications | 1 | [ ] |
| 8 | Flutter Web + Firebase Hosting deploy | 3 | [ ] |
| 9 | Polish, performance, testing, edge cases | 4 | [ ] |
| 10 | Play Store assets, submission, launch | 2 | [ ] |
| TOTAL |  | ~30 days |  |

# 13. Marketing Strategy

## 13.1 Pre-Launch (While Building)

- Build in public on Twitter/X and LinkedIn — post progress screenshots weekly

- 'Building a Wordle for news' is a one-line pitch that everyone understands

- Create a waitlist landing page on Firebase Hosting — collect emails

- Post behind-the-scenes development videos on Instagram Reels or TikTok

## 13.2 Launch Week

- Reddit — r/androidapps post with screenshots and story

- Reddit — r/InternetIsBeautiful — 'I built a daily news quiz app'

- Product Hunt — submit with a clear tagline and good screenshots

- Twitter/X thread — 'I built this in 30 days, here's how'

- LinkedIn post — professional angle on staying informed

- Personal WhatsApp + Telegram — first 50 users are people you know

## 13.3 Ongoing Growth — The Viral Loop

Every share mechanic is a free ad targeting a different audience type:

| Who Shares It | Why They Share | Who It Attracts |
| --- | --- | --- |
| Score sharers | Competitive flex | Competitive friends |
| Hot Take sharers | Debate starter | Opinion-driven people |
| Fact sharers | Interesting content | Curious learners |
| Wrapped sharers | Year-end reflection | Everyone |
| Streak sharers | Achievement pride | Habit-driven people |

The Hardest Question challenge card is the single best acquisition tool. 'Only 9% of people got this right today. Can you?' drives massive curiosity clicks from non-users.

# 14. Risks & How to Handle Them

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| AI generates a wrong answer | Medium | Flag button auto-pulls questions with 3+ reports. Daily 5-min review initially. |
| NewsData.io API goes down | Low | 3-day question buffer in Firestore. Auto-deploy backup if API fails. |
| Questions repeat | Medium | Hash every question. Check last 30 days before publishing. |
| Low initial user count | High | Seed leaderboard with placeholder data. Real rankings kick in with real users. |
| Questions feel boring | Medium | Spend Phase 1 perfecting the Gemini prompt. Run 20+ test batches. |
| App gets copied | Low | First-mover advantage + brand + streak data = strong retention moat. |
| Free tier too generous | Low | Monitor conversion rate. Adjust gate after 3 months of data. |

# 15. Start Today — Exact First Steps

Do these exact steps today. Do not skip ahead. Phase 0 takes 2-3 hours.

## Right Now — Accounts (1 hour)

- Go to console.firebase.google.com — click Create Project — name it 'briefed-app' — enable Google Analytics — done

- Go to newsdata.io — sign up for free — go to API Keys — copy your key — paste it in a notes file called keys.txt

- Go to aistudio.google.com — click Get API Key — Create API Key — copy it to the same keys.txt

- Keep keys.txt safe — never commit it to Git

## Today — Tools (1 hour)

- Install Flutter SDK from flutter.dev/docs/get-started/install — follow the guide for your OS

- Install VS Code from code.visualstudio.com

- Open VS Code — go to Extensions — search Flutter — install it — it installs Dart automatically

- Open terminal in VS Code — run: flutter doctor — fix any issues it reports

- Run: npm install -g firebase-tools

- Run: firebase login — it opens a browser — log in with your Google account

- Run: dart pub global activate flutterfire_cli

## Today — Create Project (30 mins)

- In terminal: flutter create briefed

- cd briefed

- Run: flutterfire configure — select your 'briefed-app' Firebase project — select Android and Web — done

- Run: flutter run — you should see the default Flutter counter app on your emulator

- If it runs, Phase 0 is complete. You are ready to start.

## Tomorrow — Phase 1 (2 hours)

- Open newsdata.io — go to API Playground — fetch 5 headlines for your country

- Open aistudio.google.com — create new prompt — paste system instructions from Section 7.4

- Paste your 5 headlines into the user message — click Run

- Read every question critically — is it clear, fair, interesting?

- Adjust the system instructions — run again — repeat until great

- When happy — save final prompt to quiz_prompt.txt in your project

- Phase 1 complete — start Flutter UI the next day

You have everything you need.

Start today. Ship in 30 days.

Briefed.